## Gantt & Burndown
[8 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 6
TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Project Conception and Initiation |  | 42 | 46 | -4 | 1 |  |  |  | 109.5%
Proposal of Ideas | EVERYONE | 4 | 4 | 0 | 1 | 2021-11-15 | 2021-11-21 | 7 | 100% | bar: WEEK 1 M to WEEK 1 F
Research | EVERYONE | 8 | 8 | 0 | 1 | 2021-11-22 | 2021-11-28 | 7 | 100% | bar: WEEK 2 M to WEEK 2 F
Planning | EVERYONE | 10 | 12 | -2 | 1 | 2021-11-15 | 2021-11-28 | 14 | 120% | bar: WEEK 1 M to WEEK 2 F
Scope and goals settings | EVERYONE | 6 | 6 | 0 | 1 | 2021-11-22 | 2021-11-28 | 7 | 100% | bar: WEEK 2 M to WEEK 2 F
Guidelines | EVERYONE | 4 | 6 | -2 | 1 | 2021-11-22 | 2021-11-28 | 7 | 150% | bar: WEEK 2 M to WEEK 2 F
Project Initiation | EVERYONE | 10 | 10 | 0 | 1 | 2021-11-22 | 2021-11-28 | 7 | 100% | bar: WEEK 2 M to WEEK 2 F
Skeleton of the project |  | 35 | 37 | 2 | 2 |  |  |  | 105.7%
Make up a template base for the whole app | EVERYONE | 10 | 7 | 3 | 2 | 2021-11-29 | 2021-12-05 | 7 | 70% | bar: WEEK 3 M to WEEK 3 F
Mockup of landing page | MUSERRA | 3 | 4 | -1 | 2 | 2021-11-29 | 2021-12-05 | 7 | 133.3% | bar: WEEK 3 M to WEEK 3 F
Make a scratch design | MUSERRA | 5 | 5 | 0 | 2 | 2021-11-29 | 2021-12-05 | 7 | 100% | bar: WEEK 3 M to WEEK 3 F
Setup poetry as tool managment for python | IONTA - RAZOVIC | 7 | 8 | -1 | 2 | 2021-12-06 | 2021-12-12 | 7 | 114.3% | bar: WEEK 4 M to WEEK 4 F
Poetry - Configuration fetcher API | IONTA - RAZOVIC | 7 | 9 | -2 | 2 | 2021-12-06 | 2021-12-12 | 7 | 128.6% | bar: WEEK 4 M to WEEK 4 F
Documentation | MUSERRA | 3 | 4 | -1 | 2 | 2021-12-06 | 2021-12-06 | 1 | 133.3% | bar: WEEK 4 M to WEEK 4 F
Back-end setting |  | 77 | 88 | -3 | 3 - 5 - 6 |  |  |  | 114.3%
Test auth using node,js | LAMANNA | 9 | 9 | 0 | 3 | 2021-12-13 | 2021-12-23 | 11 | 100% | bar: WEEK 5 M to WEEK 6 F
Add a persistence layer | IONTA - RAZOVIC | 11 | 13 | -2 | 3 | 2021-12-13 | 2021-12-27 | 11 | 118.2% | bar: WEEK 5 M to WEEK 6 F
Setup local REST webserver for dev API | IONTA - RAZOVIC | 10 | 10 | 0 | 3 | 2021-12-13 | 2021-12-23 | 15 | 100% | bar: WEEK 5 M to WEEK 6 F
Fetcher API | MUSERRA | 7 | 8 | -1 | 3 | 2021-12-13 | 2021-12-22 | 11 | 114.3% | bar: WEEK 5 M to WEEK 6 F
Refine authentication module | LAMANNA | 6 | 6 | 0 | 5 | 2022-01-10 | 2022-01-15 | 6 | 100% | bar: WEEK 9 M to WEEK 9 F
Exploit authentication module for securing the system | IONTA - LAMANNA - MUSERRA - RAZOVIC | 10 | 12 | -2 | 5 | 2022-01-10 | 2022-01-23 | 14 | 120% | bar: WEEK 9 M to WEEK 10 F
Call protected APIs | IONTA-RAZOVIC-SHAIDULLIN | 9 | 9 | 0 | 6 | 2022-01-24 | 2022-02-06 | 14 | 100% | bar: WEEK 11 M to WEEK 11 F
Retrive full article text on-demand | IONTA | 4 | 4 | 0 | 6 | 2022-01-24 | 2022-01-29 | 6 | 100% | bar: WEEK 12 M to WEEK 12 F
Manage duplicate in User Relation | LAMANNA | 5 | 5 | 0 | 6 | 2022-01-24 | 2022-01-28 | 4 | 100% | bar: WEEK 11 M to WEEK 11 F
Endpoint for logout | IONTA | 1 | 2 | -1 | 6 | 2022-01-31 | 2022-01-31 | 1 | 200% | bar: WEEK 12 M to WEEK 12 F
Endpoint for getting all user persisted info | IONTA | 1 | 2 | -1 | 6 | 2022-02-01 | 2022-02-01 | 1 | 200% | bar: WEEK 12 M to WEEK 12 F
Endpoint for adding a RSS Feed to a certain user | IONTA | 1 | 2 | -1 | 6 | 2022-02-02 | 2022-02-02 | 1 | 200% | bar: WEEK 12 M to WEEK 12 F
Endpoint for deleting a user | IONTA | 1 | 2 | -1 | 6 | 2022-02-03 | 2022-02-03 | 1 | 200% | bar: WEEK 12 M to WEEK 12 F
Endpoint signatures refactor | IONTA | 1 | 2 | -1 | 6 | 2022-02-04 | 2022-02-04 | 1 | 200% | bar: WEEK 12 M to WEEK 12 F
Endpoint for user sign-in from form data | IONTA | 1 | 2 | -1 | 6 | 2022-02-04 | 2022-02-05 | 1 | 200% | bar: WEEK 12 M to WEEK 12 F
Add authentication using email/password | LAMANNA - RAZOVIC - SHAIDULLIN | 4 | 4 | 0 | 6 | 2022-02-01 | 2022-02-04 | 4 | 100% | bar: WEEK 12 M to WEEK 12 F
Front-end Setting |  | 52 | 63 | -3 | 2022-05-03 |  |  |  | 121.2%
Make Feed Page | SHAIDULLIN-RAZOVIC | 5 | 5 | 0 | 3 | 2021-12-13 | 2021-12-19 | 7 | 100% | bar: WEEK 5 M to WEEK 5 F
Present feed information | SHAIDULLIN-RAZOVIC | 5 | 5 | 0 | 3 | 2021-12-13 | 2021-12-19 | 7 | 100% | bar: WEEK 5 M to WEEK 5 F
Profile page | SHAIDULLIN-RAZOVIC | 5 | 5 | 0 | 3 | 2021-12-20 | 2021-12-26 | 7 | 100% | bar: WEEK 6 M to WEEK 6 F
Login page | SHAIDULLIN-RAZOVIC | 2 | 2 | 0 | 3 | 2021-12-21 | 2021-12-26 | 6 | 100% | bar: WEEK 6 M to WEEK 6 F
Sign up page | SHAIDULLIN-RAZOVIC | 2 | 2 | 0 | 3 | 2021-12-21 | 2021-12-26 | 6 | 100% | bar: WEEK 6 M to WEEK 6 F
Manage news sources page | SHAIDULLIN-RAZOVIC | 2 | 3 | -1 | 3 | 2021-12-22 | 2021-12-26 | 4 | 150% | bar: WEEK 6 M to WEEK 6 F
Integrate in docker | SHAIDULLIN-RAZOVIC | 2 | 2 | 0 | 3 | 2021-12-27 | 2021-12-27 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
Attached ML API | SHAIDULLIN-RAZOVIC | 2 | 2 | 0 | 3 | 2021-12-27 | 2021-12-27 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
Connect to backend by means of endpoints | SHAIDULLIN-RAZOVIC | 4 | 6 | -2 | 6 | 2022-02-05 | 2022-02-06 | 2 | 150% | bar: WEEK 12 M to WEEK 12 F
Pop-up window for triggering Social Login | SHAIDULLIN-RAZOVIC | 4 | 6 | -2 | 6 | 2022-01-24 | 2022-01-26 | 2 | 150% | bar: WEEK 11 M to WEEK 11 F
Check User Authentication on the basis of Access Token | SHAIDULLIN-RAZOVIC | 5 | 8 | -3 | 6 | 2022-01-26 | 2022-01-31 | 5 | 160% | bar: WEEK 11 M to WEEK 11 F
Give the user the possibility to enter a RSS url | SHAIDULLIN-RAZOVIC | 3 | 3 | 0 | 6 | 2022-02-01 | 2022-02-03 | 2 | 100% | bar: WEEK 12 M to WEEK 12 F
Call protected APIs | SHAIDULLIN-RAZOVIC | 3 | 3 | 0 | 6 | 2022-02-02 | 2022-02-04 | 2 | 100% | bar: WEEK 12 M to WEEK 12 F
Display full text of an article | SHAIDULLIN-RAZOVIC | 1 | 1 | 0 | 6 | 2022-02-04 | 2022-02-05 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F
Attach delete user functionality | SHAIDULLIN-RAZOVIC | 2 | 3 | 1 | 6 | 2022-02-03 | 2022-02-05 | 2 | 150% | bar: WEEK 12 M to WEEK 12 F
Cleaning wired things | SHAIDULLIN-RAZOVIC | 2 | 4 | -2 | 6 | 2022-02-05 | 2022-02-06 | 1 | 200% | bar: WEEK 12 M to WEEK 12 F
Attach Change Psw Functionality | SHAIDULLIN-RAZOVIC | 1 | 1 | 0 | 6 | 2022-01-30 | 2022-02-05 | 6 | 100% | bar: WEEK 12 M to WEEK 12 F
Switch RSS feed | SHAIDULLIN-RAZOVIC | 2 | 2 | 0 | 6 | 2022-01-31 | 2022-02-03 | 3 | 100% | bar: WEEK 12 M to WEEK 12 F
Containerization |  | 23 | 31 | -8 | 4 |  |  |  | 134.8%
Setup Docker | EVERYONE | 10 | 14 | -4 | 4 | 2021-12-27 | 2022-01-05 | 10 | 140% | bar: WEEK 7 M to WEEK 8 F
Build docker img every time a push is performed | RAZOVIC | 7 | 7 | 0 | 4 | 2021-12-27 | 2021-12-30 | 4 | 100% | bar: WEEK 7 M to WEEK 7 F
Deploy docker image on remote environment | RAZOVIC | 3 | 5 | -2 | 4 | 2021-12-27 | 2022-01-02 | 7 | 166.7% | bar: WEEK 7 M to WEEK 7 F
Integrate front end in docker | RAZOVIC | 3 | 5 | -2 | 4 | 2022-01-03 | 2022-01-07 | 5 | 166.7% | bar: WEEK 8 M to WEEK 8 F
|  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
BURNDOWN DATA | TOTAL HOURS | 233 | 269 | -36 | 84 | 2.7738 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | TOTAL HOURS
[5 empty] | ^ Enter number of days |  |  |  | PLAN | 233 | 230.2262 | 227.4524 | 224.6786 | 221.9048 | 219.131 | 216.3571 | 213.5833 | 210.8095 | 208.0357 | 205.2619 | 202.4881 | 199.7143 | 196.9405 | 194.1667 | 191.3929 | 188.619 | 185.8452 | 183.0714 | 180.2976 | 177.5238 | 174.75 | 171.9762 | 169.2024 | 166.4286 | 163.6548 | 160.881 | 158.1071 | 155.3333 | 152.5595 | 149.7857 | 147.0119 | 144.2381 | 141.4643 | 138.6905 | 135.9167 | 133.1429 | 130.369 | 127.5952 | 124.8214 | 122.0476 | 119.2738 | 116.5 | 113.7262 | 110.9524 | 108.1786 | 105.4048 | 102.631 | 99.8571 | 97.0833 | 94.3095 | 91.5357 | 88.7619 | 85.9881 | 83.2143 | 80.4405 | 77.6667 | 74.8929 | 72.119 | 69.3452 | 66.5714 | 63.7976 | 61.0238 | 58.25 | 55.4762 | 52.7024 | 49.9286 | 47.1548 | 44.381 | 41.6071 | 38.8333 | 37.8333 | 35.0595 | 32.2857 | 29.5119 | 24.5119 | 21.7381 | 14.7381 | 11.9643 | 9.1905 | 6.4167 | 3.6429 | 0.86905 | -1.9048
[9 empty] | ESTIMATE | 233 | 230 | 227 | 225 | 223 | 221 | 219 | 215 | 211 | 206 | 201 | 197 | 194 | 190 | 188 | 185 | 182 | 180 | 177 | 175 | 172 | 169 | 167 | 164 | 161 | 159 | 156 | 153 | 151 | 146 | 140 | 134 | 130 | 124 | 120 | 113 | 108 | 101 | 95 | 90 | 84 | 84 | 84 | 82 | 79 | 77 | 74 | 72 | 72 | 69 | 66 | 63 | 60 | 60 | 57 | 54 | 52 | 51 | 49 | 47 | 46 | 44 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 30 | 25 | 21 | 16 | 11 | 8 | 1 | -5 | -11 | -18 | -22 | -26 | -32 | 8598
[8 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 2 | 2 | 2 | 2 | 4 | 4 | 5 | 5 | 4 | 3 | 4 | 2 | 3 | 3 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 5 | 6 | 6 | 4 | 6 | 4 | 7 | 5 | 7 | 6 | 5 | 6 | 0 | 0 | 2 | 3 | 2 | 3 | 2 | 0 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 4 | 5 | 5 | 3 | 7 | 6 | 6 | 7 | 4 | 4 | 6 | 4 | 269
[9 empty] | HRS REMAINING | 230 | 227 | 225 | 223 | 221 | 219 | 215 | 211 | 206 | 201 | 197 | 194 | 190 | 188 | 185 | 182 | 180 | 177 | 175 | 172 | 169 | 167 | 164 | 161 | 159 | 156 | 153 | 151 | 146 | 140 | 134 | 130 | 124 | 120 | 113 | 108 | 101 | 95 | 90 | 84 | 84 | 84 | 82 | 79 | 77 | 74 | 72 | 72 | 69 | 66 | 63 | 60 | 60 | 57 | 54 | 52 | 51 | 49 | 47 | 46 | 44 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 30 | 25 | 21 | 16 | 11 | 8 | 1 | -5 | -11 | -18 | -22 | -26 | -32 | -36 | 8329

## User Stories or Tasks
As a | I want to | So that | Added by | Date Added
User | Subscribe to the system | I can share my personal informations in order to let the app create my profile | EVERYONE | 2021-12-22
User | Log in the system (also with google profile) | I log in to the system and I can have access to a custom news feeds based on my preferences | EVERYONE | 2021-12-20
User | Access to my personal info | I can check and edit my personal informations or login data | EVERYONE | 2021-12-20
User | Log out from the system | I can log out from the system, using the log out button | EVERYONE | 2021-12-20
User | Delete my account | I can delete my personal info from the system, using the delete button | EVERYONE | 2021-12-21
User | Explore the feed page | I can find some news i want to read | EVERYONE | 2021-12-16
User | Read full text of a specific article | I can select a specific article and read the full text | EVERYONE | 2021-12-17
User | Obtain short summary of article content | I can obtain and read a short summary of a specific article, instead of reading the full text | EVERYONE | 2021-12-17
User | Specify an RSS url to track | I can specify an RSS url to track | EVERYONE | 2021-12-19
User | Customize as you prefered the RSS feeds | I can customize the RSS feed articles shown. | EVERYONE | 2022-02-06
User | Add RSS links | I can add a specific RSS feed which i’m interested in | EVERYONE | 2021-12-21
User | Change theme | I can change the theme's colour (light or dark), using the Theme Changer button | EVERYONE | 2021-12-19

## Product Backlog
Priority | Sprint | User Story | Task Title | Task Description | Work Estimate in hrs | GitHub Issue
1 | 3 | Subscribe and Login to the system | Authentication with oauth | Implement oauth flow | 16 | https://github.com/lrazovic/advanced_programming/issues/17
1 | 3 |  | Authentication with user password | Endpoint for register/login with user/pas, update DB | 4 | https://github.com/lrazovic/advanced_programming/issues/56
1 | 6 |  | Create and manage token | Save user token in front end local storage | 16 | https://github.com/lrazovic/advanced_programming/issues/47
2 | 3 | Access to my personal info | Profile page | Endpoint and front end page for profile | 8 | https://github.com/lrazovic/advanced_programming/issues/8
1 | 6 | Log out from the system | Logout | Delete token from front-end localstorage | 2 | https://github.com/lrazovic/advanced_programming/issues/25
1 | 6 | Delete my account | Delete user account | Delete user endpoint and update database | 2 | https://github.com/lrazovic/advanced_programming/issues/54
1 | 3 | Explore the feed page | Make Feed Page | Make feed front end page | 8 | https://github.com/lrazovic/advanced_programming/issues/24
1 | 3 |  | Present feed information | Format articles and add in the page | 8 | https://github.com/lrazovic/advanced_programming/issues/4
1 | 3 |  | Fetcher Api | Implement script to fetch rss feeds | 8 | https://github.com/lrazovic/advanced_programming/issues/12
2 | 6 | Read full text of an article | Extend article text | Obtain full text of the article | 1 | https://github.com/lrazovic/advanced_programming/issues/43
1 | 3 | Obtain short summary of article content | Implement ML module to get summary | ML python module to get the summary of the article | 16 | https://github.com/lrazovic/advanced_programming/issues/13
2 | 6 | Customize as you prefered the RSS feeds | Possibility to add custom rss link | Add endpoint for add rss feeds and update database design | 16 | https://github.com/lrazovic/advanced_programming/issues/53